## Test cases
Test Case | Description | Expected output | Real output
1 | Try to press any button expect 1,2,3 | Not allowed | Not allowed
2 | Try to increase Temperature and set new temperature in the system | Pass | Pass
3 | Temperature is higher than set temperature | Buzzer start work | buzzer start work
4 | Temperature is lower than set temperature | Buzzer stop | buzzer stop
5 | Try to change set temperature higher than 35 C | Not allowed | Not allowed
6 | Try to change set temperature lower than 18 C | Not allowed | Not allowed
7 | Press the reset button | Ready to receive new set temperature | Ready to receive new set temperature
8 | Test timeout | Pass | Pass

## Team backlog
| Task Name | Assigned | Exepected Time To Finish | Actual Time To Finish
1 | LCD_DESIGN | Mohamed Abdelsalam | 1h | 45min
2 | LCD_DRIVER | Mohamed Abdelsalam | 6h | 20h
3 | LCD_TESTING | Mohamed Abdelsalam | 3h | 7h
4 | KEYPAD_DESIGN | Mohamed Sayed | 2h | 2.5h
5 | KEYPAD_DRIVER | Mohamed Sayed | 1.5h | 2h
6 | KEYPAD_TESTING | Mohamed Sayed | 30min | 30min
7 | ADC_DESIGN | Ebrahem Mostafa | 30min | 30min
8 | ADC_DRIVER | Ebrahem Mostafa | 3h | 4h
9 | ADC_TESTING | Ebrahem Mostafa | 45min | 30min
10 | BUZZER_DESIGN | Ebrahem Mostafa | 15min | 15min
11 | BUZZER_DRIVER | Ebrahem Mostafa | 15min | 15min
12 | BUZZER_TESTING | Ebrahem Mostafa | 10min | 10min
13 | TEMPERATURE_DESIGN | Ebrahem Mostafa | 30min | 30min
14 | TEMPERATURE_DRIVER | Ebrahem Mostafa | 15min | 15min
15 | TEMPERATURE_TESTING | Ebrahem Mostafa | 15min | 15min
16 | APP_DESIGN | Mohamed Sayed | 30min | 30min
17 | APP_DRIVER | Mohamed Sayed | 2h | 3h
18 | APP_TESTING | Mohamed Sayed | 5h | 8h
19 | Documentation | team | 3h | 5h
20 | Integrate all Drivers | team | 2h | 2.5h